## Slide 1
DAM REHABILITATION AND IMPROVEMENT PROJECT II & III
(09-04-2024)
Procurement of Works- National Competitive Bidding-I (Preparation of bid documents-Important Provisions of ITB/BDS and GCC/PCC)
Santosh K Singh
9899866627, santoshkumar.singh@smec.com

## Slide 2: Procedural requirements
GFR Provisions: Chapter 10 : Budgeting And Accounting Of Externally Aided Projects
Rule 264 (3) The Department of Economic Affairs, Ministry of Finance as the nodal agency shall execute the legal agreement for loans or grants from external funding Agency(ies).
Chapter 11 GOVERNMENT GUARANTEES:
(1) Power to Give and Limits on Government Guarantees. The power of the Union Government to give guarantees emanates from and is subject to such limits as may be fixed in terms of Article 292 of the Constitution of India.
  O b j e c t i v e s o f G o v e r n m e n t Guarantees: To fulfil the requirement in cases where sovereign guarantee is a precondition for concessional loans from bilateral/ multilateral agencies t o c e n t r a l p u b l i c s e c t o r companies/agencies.
  CVC Circular No. 98/ORD/001 dated 28.10.2011 “ It is clarified that the commission’s guidelines would not be applicable in projects funded by the World Bank, ADB, etc., if found to be in conflict with the applicable procurement rules of the funding agencies“
  World Bank’s “Procurement Regulations for IPF Borrowers, July 2016,_Revised August 2018
Dam Rehabilitation And Improvement Project II & III

## Slide 3: Procurement Cycle and Planning
Preparation and approval of PST
PP to be declared and got approved in STEP
Preparation and Issue of Bidding Documents
Pre bid meeting and issue of its minutes
Receiving of Bids and Bid Opening Technical part
Technical Bid Evaluation
Financial Bid opening of technically qualified bidders.
Negotiation and Award of Contract
Contract signing and Commencement of Works
Contract Management
Dam Rehabilitation And Improvement Project II & III

## Slide 4: Preparation of bid document-NCB
Threshold limits for NCB is USD 1,00,000-USD 40 million (INR 70 Lac -280 Cr). Above this ICB is to be used.
Standard NCB bid document as shared by CPMU is to be used.
CPMU document review threshold for works is USD 5-10 million (INR 35-70 Cr)
Procurement of works above USD 10 million (INR 70 Cr) comes under Prior Review of the Bank and Bank’s no objection is required at each stages of the procurement process.
CPMU will have only an advisory role in procurement except that all procurements subject to prior review, will be sent to the Bank only through the CPMU.
Text in Italics given in standard document is/are instructions / guidelines for respective clause/ Sub-clause. The same to be deleted from final bid document.
Approved World Bank compliant e-procurement is to be used for e-tendering.
Minimum 30 days' time from date of publication is to be given for submission of bids. Even in cases of re-bidding also this is to be followed.
Dam Rehabilitation And Improvement Project II & III

## Slide 5: Preparation of bid document-ncB
Last date of bid submission and date of opening of bid shall be the same.
Bid submission start date should be nearest to the bid submission last date.
NO CHANGES TO BE MADE IN ITB and GCC. Only corresponding sections of BDS and PCC to be used for giving required specific details.
Abridged version of NIT to be published in News Paper and posted on department’s website for information of prospective bidders.
Cost of the bidding documents to be kept NIL or nominal.
Provision for Pre-bid meeting is to be made after 7-10 days of publication.
Minutes of Pre-bid meeting along with Amendments, if any, without disclosing the names of bidders to be timely uploaded in the procurement portal.
Prospective Bidders to be given reasonable time to take an addendum into account in preparing their Bids (10-14 days).
Private entity, or a state-owned enterprise or institution subject to ITB 4.6, or any combination of them in the form of a joint venture (JV) may be allowed to bid.
Dam Rehabilitation And Improvement Project II & III

## Slide 6: Preparation of bid document
ITB 4.6 Bidders that are state-owned enterprises or may be eligible to compete and be awarded a Contract(s) only if they can establish, that they (i) are legally and financially autonomous (ii) operate under commercial law, and (iii) are not under supervision of the Employer.
The Technical Part shall not include any information related to the Bid price.
Financial Envelop must have provision for uploading Letter of Bid – Financial Part in pdf format.
It is advised to keep bid validity period as 90 days.
In exceptional circumstances, prior to the expiration of the Bid validity period bidders may be requested to extend the bid validity period and validity of Bid Security for 45 days beyond extended validity period.
Bidders may refuse to extend validity period of their bid without forfeiting their bid security.
In case award is delayed by a period exceeding 56 days beyond the initial validity period bid price shall be adjusted by @ 3-5% per annum in cases of fixed price contracts.
Dam Rehabilitation And Improvement Project II & III

## Slide 7: Bid SECURITY
Bid security should be in the range of 1-2% of the estimated value of the work.
World Bank allows bid security to be submitted in form of bank guarantee and Demand Draft issued by a Nationalized or Scheduled bank located in India;
Departments may allow other modes of bid security if specified in the BDS.
Only Online deposit of bid security should not be insisted.
Bid Security shall have to be valid for 45 days beyond the validity of the bid
Bid securities submitted in form of DD must be deposited in the bank account
Bids not accompanied by a substantially responsive Bid Security shall be rejected by the Employer as non-responsive.
The Bid Security may be forfeited (a) if a bidder withdraws its bid (b) if successful bidder fails to sign the contract or fails to furnish performance security.
The Bid Security of a JV shall be in the name of the JV that submits the Bid.
All the Bid Securities/Performance securities submitted must be got verified from the issuing banks/post offices.
Bid Security of unsuccessful Bidders shall be returned as promptly as possible upon the successful Bidder’s signing the Contract and furnishing the Performance Security.
Dam Rehabilitation And Improvement Project II & III

## Slide 8: Signing and submission of bids
The Bid shall be signed by a person duly authorized to sign on behalf of the Bidder. This authorization shall consist of a written confirmation as specified in the BDS and shall be uploaded along with the Bid.
In case the Bidder is a JV, the Bid shall be signed by an authorized representative of the JV on behalf of the JV, and so as to be legally binding on all the members as evidenced by a power of attorney signed by their legally authorized representatives.
Bids, both Technical and Financial Parts, shall be submitted online on the e-procurement portal only no later than the date and time specified in the BDS.
The completed bid comprising of documents indicated in ITB 12, should be uploaded on the e-procurement portal along with scanned copies of requisite certificates.
Physical, e-mail, Telex, Cable or Facsimile bids will be rejected as non-responsive.
The Employer shall publicly open Technical Parts of all Bids received by the deadline, at the date, time and place specified in the BDS.
Dam Rehabilitation And Improvement Project II & III

## Slide 9: Evaluation of bids
Information relating to the evaluation of Bids and recommendation of contract award, shall not be disclosed to Bidders or any other persons not officially concerned with the Bidding process until information on Intention to Award the Contract is transmitted to all Bidders.
27.Clarification of Bids: To assist in the examination, evaluation, and comparison of the Bids, and qualification of the Bidders, the Employer may, at its discretion, ask any Bidder for a clarification of its Bid giving a reasonable time for a response. Any clarification submitted by a Bidder that is not in response to a request by the Employer shall not be considered. The Employer’s request for clarification and the response shall be in writing.
If a Bidder does not provide clarifications of its Bid by the date and time set in the Employer’s request for clarification, its Bid may be rejected.
ITB 29 Provided that a Bid is substantially responsive, the Employer may waive any nonmaterial nonconformities in the Bid which do not constitute a material deviation, reservation or omission.
Dam Rehabilitation And Improvement Project II & III

## Slide 10: Evaluation of bids
If a Bid is substantially responsive, the Employer may request the Bidder to submit the necessary information or documentation, within a reasonable period, to rectify nonmaterial nonconformities in the Bid related to documentation requirements. Failure of the Bidder to comply with the request may result in the rejection of its Bid.
In evaluating the Technical Parts of each Bid, the Employer shall use the criteria and methodologies listed in this ITB and Section III, Evaluation and Qualification Criteria. No other evaluation criteria or methodologies shall be permitted.
The Employer’s determination of a Bid’s responsiveness is to be based on the contents of the Bid itself, as defined in ITB 11.
If a Bid is not substantially responsive to the requirements of the bidding document, it shall be rejected by the Employer.
A material deviation, reservation, or omission is one that: affect the scope, quality, or performance of the Works or inconsistent with the bidding document, the Employer’s rights or the Bidder’s obligations or if rectified, would unfairly affect the competitive position of other Bidders presenting substantially responsive Bids
Dam Rehabilitation And Improvement Project II & III

## Slide 11: Qualification of bidders
The Employer shall determine to its satisfaction whether the eligible Bidders that have submitted substantially responsive Bid meet the qualifying criteria specified in Section III, Evaluation and Qualification Criteria.
The determination shall be based upon an examination of the documentary evidence of the Bidder’s qualifications submitted by the Bidder, pursuant to ITB 17.
Bid once rejected by the Employer may not subsequently be made responsive
Only Bids that are both substantially responsive to the bidding document and meet all Qualification Criteria shall have the Financial Parts of their Bids opened at the second public opening. Financial Bids are to be opened 7 days after uploading the results technical evaluation.
Following the completion of the Technical evaluation of the Bids, the Employer shall notify in writing those Bidders whose Bids were considered non-responsive giving reasons for disqualification.
Dam Rehabilitation And Improvement Project II & III

## Slide 12: Bid Data sheet (BDS)
Specific data for the works to be procured shall complement, supplement or amend the provisions in the ITB.
BDS will have specific information only against those ITB clauses in which it is specified “as specified in the BDS”
Against ITB 4.1 if JVs are permitted ‘Yes’ to be selected and max number of members allowed in the JV to be mentioned (2 or 3).
Bids submitted by a JV (where permitted) shall include a copy of the JV Agreement entered into by all members. Alternatively, a letter of intent to execute a JV Agreement together with a copy of the proposed Agreement.
ITB7.4 Pre-bid meeting should be held, and minutes issued 2 weeks before the deadline for submission and before start date of submission.
ITB 8.1At any time prior to the deadline for submission of bids, the Employer may amend the bidding document by issuing addenda and the same will part of the bidding document.
Dam Rehabilitation And Improvement Project II & III

## Slide 13: Bid Data sheet (BDS)-Documents to be submitted
ITB 11 is an important section of ITB/BDS. Employer can add other documents required in respective BDS (Technical and Financial parts)
The Bid shall comprise two Parts, namely the Technical Part and the Financial Part to be submitted simultaneously in the portal.
Letter of Bid – Technical Part
Bid Security
Alternative Bid – Technical Part (Not permitted)
Authorization: written confirmation authorizing the signatory of the Bid
Bidder’s Eligibility
Qualifications
Conformity: statement of work methods, equipment, personnel, schedule and any other information as stipulated in Section IV.
Construction methodology
Contractor Registration certificate (as per RFB); and
(j) any other document required in the BDS.
Dam Rehabilitation And Improvement Project II & III

## Slide 14: Bid Data sheet (BDS)-Documents to be submitted
ITB 11.3 The Financial Part shall contain the following:
Letter of Bid – Financial Part
Completed Schedules including priced Bill of Quantities
Alternative Bid - Financial Part: Not permitted
any other document required in the BDS.
The Technical Part shall not include any information related to the Bid price. Where material financial information related to the Bid price is contained in the Technical Part the Bid shall be declared non-responsive.
Bids submitted by a JV, if permitted, shall include JV Agreement or letter of intent to execute a JV Agreement in the event of a successful bid.
Additional documents may include Contractor Registration certificate on e-procurement system as per RFB, if applicable, Code of Conduct for Contractor’s Personnel (ES), Management Strategies and Implementation Plans (MSIP) to manage the (ES) risks, etc as suggested in SBD.
Dam Rehabilitation And Improvement Project II & III

## Slide 15: Bid Data sheet (BDS)-Documents to be submitted
ITB 12.3 Submission of Original Documents: The bidders are required to separately submit:
original payment documents towards the cost of bid document; and registration on e-procurement website (if applicable);
original bid security in approved form; and
original affidavit regarding correctness of information furnished with bid document, with the office specified in the BDS
Complete address of the Employer to be given in BDS for submission of original documents.
Original documents are to be submitted before the Bid submission deadline, either by registered/speed post/courier or by hand, failing which the bids will be declared non-responsive and will not be opened.
Hard copy of rest of the bid or any other document are not to be submitted.
Dam Rehabilitation And Improvement Project II & III

## Slide 16: Bid Data sheet (BDS)
ITB 13.1 Alternative Bids shall not be permitted.
ITB 13.2 Alternative times for completion shall not be permitted.
ITB 13.4 Alternative technical solutions shall be permitted for the following parts of the Works: Not Applicable
ITB 14.5 The prices quoted by the Bidder Shall be / Shall not be subject to adjustment during the performance of the Contract.
Price adjustment is mandatory for all contract with completion time exceeding 18 months. In such cases “Shall be” to be selected.
In case completion time is less than 18 months “Shall not be” to be retained.
The adjustment of contract price, if provided, will be done in accordance with GCC Clause 49 and corresponding provisions under PCC and Appendix 2 to PCC.
ITB 18.1 Period of Validity of Bids: It is advised to keep this period as 90 days.
Bid valid for a shorter period shall be rejected by the Employer as nonresponsive.
ITB 18.3 The Bid price shall be adjusted by the following factor: 3% per annum.
Dam Rehabilitation And Improvement Project II & III

## Slide 17: Bid Data sheet (BDS)
ITB 19.1 Bid Security: Bid Security should be in the range of 1-2% of the of the estimated value of the work. However, amount should be written in INR.
ITB 19.3 Allows bid security to be submitted in forms of (a) an unconditional bank guarantee (b) an irrevocable letter of credit and (c) a cashier’s or certified check or demand draft.
ITB 19.3 (d) another security specified in the BDS
Other types of acceptable securities in BDS may include Fixed Deposit/Time Deposit certificate issued by a Nationalized or Scheduled Bank located in India.
All the Bid Securities submitted must be got verified from the issuing banks/post offices.
The Bid Security shall be valid for forty-five (45) days beyond the original validity period of the Bid, or beyond any period of extension if requested under ITB 18.2.
ITB 19.4 Bid not accompanied by a substantially responsive Bid Security or Bid Securing Declaration shall be rejected
Dam Rehabilitation And Improvement Project II & III

## Slide 18: Bid Data sheet (BDS)
ITB 20.3 The Bid shall be signed by a person duly authorized to sign on behalf of the Bidder.
The written confirmation of authorization to sign on behalf of the Bidder shall consist of:
Legally valid Power of Attorney is required to demonstrate the authority of the signatory to sign the Bid; and
In the case of Bids submitted by an existing or intended JV, if permitted as per ITB 4.1, the authorization shall be evidenced by a Power of Attorney signed by legally authorized signatories of all the members
ITB 20.4 In case the Bidder is a JV, the Bid shall be signed by an authorized representative of the JV on behalf of the JV and so as to be legally binding on all the members as evidenced by a power of attorney signed by their legally authorized representatives. Documents establishing authority to sign the bid on behalf of the JV shall be uploaded along with the bid.
Dam Rehabilitation And Improvement Project II & III

## Slide 19: Bid Data sheet (BDS)
ITB 22.1 The deadline for uploading the Bids will be at least 30 days after its publication.
ITB 25.1 The online Bid opening date of Technical Parts of Bids should be the same as the deadline for submission of bids. The time should be promptly after the time fixed for bid submission.
ITB 34.2 ©: After completion of technical evaluation of bids, the employer will notify bidders of date and time of opening of financial bids of qualified bidders.
The Financial Parts of the bids shall not be opened earlier than seven (7) days from the communication of technical evaluation results to the bidders.
ITB 39.1 The Employer shall compare the evaluated costs of all responsive and qualified Bids to determine the Bid that has the lowest evaluated cost.
ITB 47.1 Notification of Award: Prior to the expiration of the Bid Validity Period, the Employer shall transmit the Letter of Acceptance to the successful Bidder.
Within ten (10) Business Days after the date of transmission of the Letter of Acceptance, the Employer shall publish the Contract Award Notice
Dam Rehabilitation And Improvement Project II & III

## Slide 20: Bid Data sheet (BDS)
ITB 49.1 Promptly upon Notification of Award, the Employer shall prepare the Contract Agreement, and keep it ready in the office of the Employer for the signature of the Employer and the successful Bidder, within 21 days following the date of Letter of Acceptance.
ITB 50.1 Performance Security: Within twenty-one (21) days of the receipt of the Letter of Acceptance from the Employer, the successful Bidder shall furnish the Performance Security and the Environmental and Social (ES) Performance Security.
ITB 51.1 Adjudicator: Name of the proposed adjudicator and reimbursable expenses are required to be mentioned in the BDS.
Dam Rehabilitation And Improvement Project II & III

## Slide 21: Bidding Forms
Letter of Bid-Technical: This letter must be on bidder’s letter head having name and address.
Technical Proposal Forms:
Forms of Personnel: Bidders should provide the names and details of the suitably qualified Key Personnel to perform the Contract. The data on their experience should be supplied using the Form PER-2 for each candidate.
Forms for Equipment: A separate Form shall be prepared for each item of equipment.
Site Organization : Bidder must furnish site organization here.
Method Statement: Detailed note should be submitted outlining bidders proposed methodology and program of construction including Contractor’s Environmental and Social, Health Management Strategies and Implementation Plans (ES-MSIP).
Mobilization Schedule
Construction Schedule
Environmental and Social, Health Management Strategies and Implementation Plans
Dam Rehabilitation And Improvement Project II & III

## Slide 22: Bidding Forms
Form FIN – 3.1: Financial Situation and Performance
Form FIN - 3.2: Average Annual Construction Turnover: Annual construction turnover calculated as total certified payments received for work in progress or completed, for 7 years. This should be certified by a Chartered Accountant.
JOINT VENTURE (Where permitted as per BDS ITB 4.1)
Form FIN - 3.3: Financial Resources:
Format for evidence of access to or availability of cash flow: To be given from a Nationalized or Scheduled Bank in India specifically for the work for which bid is submitted.
Form EXP - 4.1: General Construction Experience
Form EXP - 4.2(a): Specific Construction and Contract Management Experience
Form EXP - 4.2(b): Construction Experience in Key Activities
Form of Bid Security - Bank Guarantee
Affidavit regarding correctness of information provided
Dam Rehabilitation And Improvement Project II & III

## Slide 23: Bidding Forms
Letter of Bid - Financial Part
Bill of Quantities: Item wise rates are to be quoted. Rates quoted will be inclusive of all taxes. List of items with unit and quantities are to be provided by the employer.
PART 2 – Works’ Requirements: This part includes Works’ Requirements, Specifications, Environmental and Social Requirements, Drawings, Supplementary Information: Are to be provided by the Employer in the bid document.
Dam Rehabilitation And Improvement Project II & III

## Slide 24: Important conditions of Gcc/PCC
General Conditions of Contract (GCC), read in conjunction with the Particular Conditions of Contract (PCC) and other documents listed therein, should be a complete document expressing fairly the rights and obligations of both parties.
GCC 1.1(v) Intended Completion Period: To be specified in PCC. In cases of sectional completion or milestones, those dates should also be listed in PCC.
GCC 1.1 (dd) Start Date: It shall be 10 days after the date of issue of notice to proceed with works.
GCC 2.2 Sectional Completion: Milestone wise time of completion are to be inserted in PCC, if applicable.
GCC 2.3 Documents forming the Contracts: Agreement, Letter of Acceptance, Contractor’s Bid, Particular Conditions of Contract, General Conditions of Contract, including Appendices, Specifications, Drawings, Bill of Quantities, and any other document listed in the PCC as forming part of the Contract.
Dam Rehabilitation And Improvement Project II & III

## Slide 25: Important conditions of Gcc/PCC
GCC 13.1 Insurance: The Contractor shall provide, in the joint names of the Employer and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts and deductibles stated in the PCC.
Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for the Project Manager’s approval before the Start Date.
In case contractor fails to submit insurance papers, appropriate amount as indicated in PCC to be deducted from the bill.
GCC 20.1 Possession of the Site:The Employer shall give possession of all parts of the Site to the Contractor. If possession of a part is not given by the date stated in the PCC, the Employer shall be deemed to have delayed the start of the relevant activities, and this shall be a Compensation Event.
GCC 23 Appointment of the Adjudicator: The Adjudicator shall be appointed jointly by the Employer and the Contractor, at the time of the Employer’s issuance of the Letter of Acceptance.
Either party may refer a decision of the Adjudicator to an Arbitrator within 28 days of the Adjudicator’s written decision.
Dam Rehabilitation And Improvement Project II & III

## Slide 26: Important conditions of Gcc/PCC
GCC 31.1.Extension of the Intended Completion Date: The Project Manager shall extend the Intended Completion Date including milestones if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date as per the agreed milestones.
Decision on extension of the completion must be taken before expiry of the intended completion date.
GCC 31.2 The Project Manager shall decide whether and by how much to extend the Intended Completion Date within 21 days of the Contractor asking the Project Manager for a decision upon the effect of a Compensation Event or Variation and submitting full supporting information. If the Contractor has failed to give early warning of a delay or has failed to cooperate in dealing with a delay, the delay by this failure shall not be considered in assessing the new Intended Completion Date.
GCC 33.1 The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works
GCC 34.1 “Either the Project Manager or the Contractor may require the other to attend a management meeting held periodicity. The business of a management meeting shall be to review the progress of construction.
Dam Rehabilitation And Improvement Project II & III

## Slide 27: Important conditions of Gcc/PCC
GCC 34.1 “Either the Project Manager or the Contractor may require the other to attend a management meeting held periodicity. The business of a management meeting shall be to review the progress of construction.
GCC 38.1 Defects Liability Period: This period is usually between 6-12 months and begins at completion. During this period, the Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period. The Defects Liability Period shall be extended for as long as Defects remain to be corrected.
GCC 40.1 Contract Price: The Bill of Quantities shall contain priced items for the Works to be performed by the Contractor. The Bill of Quantities is used to calculate the Contract Price.
For Works contract price is inclusive of all taxes as applicable.
GCC 41.1 Changes in the Contract Price: If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than 25 percent, provided the change exceeds 1 percent of the Initial Contract Price, the Project Manager shall adjust the rate to allow for the change.
Dam Rehabilitation And Improvement Project II & III

## Slide 28: Important conditions of Gcc/PCC
(a) If the quantity of work executed exceeds the quantity of the item in BOQ beyond the higher specified limit the Project Manager shall fix the rate to be applied for the additional quantity of the work executed.
(b) If the quantity of work executed is less than the quantity of the item in BOQ and is lesser than the lower specified limit, the Project Manager shall fix the rate to be applied for whole of the quantity of the work so executed.
GCC 41.2 The Project Manager shall not adjust rates from changes in quantities if thereby the Initial Contract Price is exceeded by more than 15 percent, except with the prior approval of the Employer.”
GCC 42 Variations: The Contractor shall provide the Project Manager with a quotation for carrying out the Variation.
If the Contractor’s quotation is unreasonable, or if contractor fails to provide the Project Manager with a quotation within a reasonable time, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs.
Dam Rehabilitation And Improvement Project II & III

## Slide 29: Important conditions of Gcc/PCC
GCC 44.1Paymwnt Certificates: The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed less the cumulative amount certified previously, along with details of measurement of the quantity of works executed in a tabular form approved by the Project Manager.
44.2 The Project Manager shall check the Contractor’s monthly statement and certify the amount to be paid to the Contractor, after taking into account any credit or debit for the month in question in respect of materials for the works in the relevant amount and under conditions set forth in GCC Sub-Clause 53.1 (Secured Advance).
GCC 45 Payments: Payments shall be adjusted for deductions for advance payments, retention, other recoveries in terms of contract & taxes to be deducted at source [TDS] as per applicable law. The Employer shall pay the Contractor the amounts certified by the Project Manager within 28 days of the date of each certificate.
If the Employer makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the rate of 3-5% per annum.
Dam Rehabilitation And Improvement Project II & III

## Slide 30: Important conditions of Gcc/PCC
GCC 45 Payments: Payments shall be adjusted for deductions for advance payments, retention, other recoveries in terms of contract & taxes to be deducted at source [TDS] as per applicable law. The Employer shall pay the Contractor the amounts certified by the Project Manager within 28 days of the date of each certificate.
If the Employer makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the rate of 3-5% per annum.
GCC 45.4 Items of the Works for which no rate or price has been entered in shall not be paid for by the Employer.
GCC 46 Compensation Events: (a) The Employer does not give access to a part of the Site by the Site Possession Date (c) The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time (d) The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects (i) The advance payment is delayed.
Dam Rehabilitation And Improvement Project II & III

## Slide 31: Important conditions of Gcc/PCC
GCC 47.1 Tax: The rates quoted by the Contractor shall be deemed to be inclusive of the GST and other taxes that the Contractor will have to pay for the performance of this Contract. The Employer will perform such duties in regard to the deduction of such taxes at source [TDS] as per applicable law.”
GCC 47.2 The Project Manager shall adjust the Contract Price if taxes, duties, and other levies are changed between the deadline for the submission of bids for the Contract and the date of the last Completion certificate.
GCC 49 Price Adjustment: Prices shall be adjusted for fluctuations in the cost of inputs only if provided for in the PCC. This is used only when intended completion period is more than 18 months.
GCC 50.1 Retention Money: Retention Money shall be 6% from each bill subject to the maximum of 5% of final contract price. Max 10%.
On completion half of the retention money shall be repaid and half after successful completion of defects liability period. On completion of the whole works the Contractor may substitute the balance retention money with an “on demand” Bank guarantee.
Dam Rehabilitation And Improvement Project II & III

## Slide 32: Important conditions of Gcc/PCC
GCC 51 Liquidated Damage: The Contractor shall pay liquidated damages to the Employer at the rate per day stated in the PCC for each day that the Completion Date is later than the Intended Completion Date (for the whole of the works or the milestones as stated in the PCC) . The total amount of liquidated damages shall not exceed the amount defined in the PCC. The Employer may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities.
GCC 51.2 If the Intended Completion Date including milestones is extended after liquidated damages have been paid, the Project Manager shall correct any overpayment of liquidated damages by the Contractor by adjusting the next payment certificate. The Contractor shall be paid interest on the overpayment, calculated from the date of payment to the date of repayment, at the rates specified in GCC Sub-Clause 45.1.
Usually, Liquidated Damages are set between 0.05-0.20 % per day and total amount not to exceed between 5-10% of the contract price.
Dam Rehabilitation And Improvement Project II & III

## Slide 33: Important conditions of Gcc/PCC
GCC 52 Bonus: Not to be used.
GCC 53 Advance Payment: The Employer shall make advance payment to the Contractor of the amounts stated in the PCC by the date stated in the PCC, against provision by the Contractor of an Unconditional Bank Guarantee in amounts and currencies equal to the advance payment.
The Project Manager shall make advance payment in respect of materials intended for but not yet incorporated in the Works in accordance with conditions stipulated in the PCC.
USUALLY, EQUIPMENT AND SECURED ADVANCES ARE NOT ENVISAGED IN REHABILITATION WORKS. ACCORDINGLY MENTION “NA” UNDER RELEVENT COLUMNS
Hence, only Mobilization Advance @ 5% of the contract price to be paid as per PCC.
The advance shall be repaid with percentage deductions from the interim payments certified by the Project Manager under the Contract.
Dam Rehabilitation And Improvement Project II & III

## Slide 34: Important conditions of Gcc/PCC
GCC 54 Performance Security: The Performance Security and an Environmental and Social (ES) Performance Security shall be provided to the Employer no later than the date specified in the Letter of Acceptance and shall be issued in the amounts specified in the PCC and shall be issued by a Nationalized or Scheduled bank in India. The Performance Security including additional security for unbalanced bids, and the ES Performance Security, shall be valid until a date 28 days from the date of issue of the Certificate of Completion.
Performance Security submitted by the contractor must be got verified from the issuing bank.
Performance Security; additional Performance Security for bids which are seriously unbalanced, front-loaded or substantially below updated estimates; and ES Performance Security shall normally not exceed 20 % of the Accepted Contract Amount.
In cases of HM and supply and installation works having defects liability period> 12 months percentage of performance security must be kept on higher side.
Dam Rehabilitation And Improvement Project II & III

## Slide 35: Important conditions of Gcc/PCC
GCC 61 Termination: The Employer or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract.
61.2 Fundamental breaches of Contract shall include, but shall not be limited to, the following:
(a) the Contractor stops work for 28 days when no stoppage of work is shown on the current Program and the stoppage has not been authorized by the Project Manager;
(b) the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within 28 days;
(d) a payment certified by the Project Manager is not paid by the Employer to the Contractor within 84 days of the date of the Project Manager’s certificate;
(e) the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager;
Dam Rehabilitation And Improvement Project II & III

## Slide 36: Important conditions of Gcc/PCC
(f) the Contractor does not maintain a Security, which is required;
(g) the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the PCC;
(h) if the Contractor, in the judgment of the Employer has engaged in Fraud and Corruption
The contractor has contravened Clauses 7 and 9 of GCC.
The contractor does not adhere to the agreed construction program, agreed ES-MSIP [Clause 30 of GCC], and also fails to take satisfactory remedial action as per agreements reached in the management meetings [Clause 30 of GCC] for a period of 60 days
(k) The contractor fails to carry out the instructions of the Project Manager within a reasonable time determined by the Project Manager in accordance with GCC Clause 15.1 and 22.
(l) The contractor (in case of Joint Venture) has modified the composition of the joint venture and/or the responsibility of each member of the joint venture from what is stated in joint venture agreement without the prior approval of the Employer
Dam Rehabilitation And Improvement Project II & III

## Slide 37: Important conditions of Gcc/PCC
61.3 Notwithstanding the above, the Employer may terminate the Contract for convenience.
61.4 If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible.
61.5 When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under GCC Sub-Clause 61.2 above, the Project Manager shall decide whether the breach is fundamental or not.
GCC 62 Payment upon Termination: If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed plus additional 20%, as specified in the PCC. Additional Liquidated Damages shall not apply. If the total amount due to the Employer exceeds any payment due to the Contractor, the difference shall be a debt payable to the Employer.
Dam Rehabilitation And Improvement Project II & III

## Slide 38: Important conditions of Gcc/PCC
62.2 If the Contract is terminated for the Employer’s convenience or because of a fundamental breach of Contract by the Employer, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate.
GCC 66 Force Majeure: exceptional event or circumstance which is beyond a Party's control. This may include, but not limited to:
(i) war, hostilities
(ii) rebellion, terrorism, revolution, insurrection, military or usurped power, or civil war
(iii) riot, commotion, disorder, strike or lockout by persons other than the Contractor's Personnel
(v) natural catastrophes such as earthquake, hurricane, typhoon or volcanic activity.
(vi) Spread of any Pandemic diseases
Dam Rehabilitation And Improvement Project II & III

## Slide 39: Important conditions of Gcc/PCC
GCC 66.4 Consequences of Force Majeure: If the Contractor is prevented from performing any of his obligations under the Contract by Force Majeure of which notice has been given, the contractor shall be entitled to: an extension of time for any such delay, if completion is delayed, under Extension of the Intended Completion Date.
Annexures/Appendix to GCC/Contract:
APPENDIX A TO GENERAL CONDITIONS: Fraud and Corruption (Not to be modified)
APPENDIX B: Environmental and Social (ES) Metrics for Progress Reports (May be amended to reflect specific requirements of the contract.
Section IX - Particular Conditions of Contract: Except where otherwise specified, all Particular Conditions of Contract should be filled in by the Employer prior to issuance of the bidding document.
Appendix 1: Salient Features of Labour & Environment Protection Laws: This list is only illustrative and not exhaustive. Bidders and Contractors are responsible for checking the correctness and completeness of the list. The law as current on the date of bid opening will apply.
Dam Rehabilitation And Improvement Project II & III

## Slide 40: Important conditions of Gcc/PCC
Salient Features Of Some Of The Major Laws That Are Applicable For Protection Of Environment
Appendix 2 Tables of Adjustment Data, wherever applicable
BOQ SCHEDULES
Appendix - 3 Appointment of Adjudicator: Suggested letter of appointment
Summary Of Ajudicator’s Responsibilities
Sample Format of Adjudicator’s Recommendation
Section X - Contract Forms:
Notification Of Award Letter of Acceptance :on letterhead paper of the Employer
Issue of Notice to proceed with the work: on letterhead paper of the Employer
Contract Agreement
Performance Security - Bank Guarantee (including additional performance security)
Environmental and Social (ES) Performance Security: ES – Bank Guarantee
Advance Payment Security :Demand Guarantee
Retention Money Security: Demand Guarantee
Dam Rehabilitation And Improvement Project II & III

## Slide 41: That’s ALL FOR NOW
© Santosh K. Singh
Dam Rehabilitation And Improvement Project II & III